## Worksheet
Task | Responsible Person | Start Date | End Date | Status | Resources Required
Project Initiation | John Smith | 2024-01-01 | 2024-01-15 | In Progress | Project Manager, Budget Analyst
Requirements Gathering | Sarah Lee | 2024-01-16 | 2024-02-05 | Pending | Business Analysts, Stakeholders
Design Phase | Michael Chen | 2024-02-06 | 2024-03-15 | Not Started | UI/UX Designer, Technical Lead
Development Phase | Linda Park | 2024-03-16 | 2024-06-30 | Planned | Software Developers, QA Team
Testing & Deployment | David Wu | 2024-07-01 | 2024-07-31 | Not Started | QA Engineers, DevOps Team
Post-Launch Review | All Project Team | 2024-08-01 | 2024-08-15 | Pending | Project Manager, Operations Team