## Worksheet
Startup Project Plan - Resource Planning
Project Phase | Objective | Key Activities | Resource Requirements | Timeline (Weeks) | Status
Discovery & Feasibility | Validate market need and technical feasibility. | Market research, user interviews, prototype design. | 3 developers, 1 UX designer, 1 business analyst. | 4 | In Progress
Product Design | Create wireframes and user flows for core features. | Design sprints, usability testing, UI development. | 1 UX designer, 2 UI artists, 1 product manager. | 6 | Pending Start
Development (MVP) | Build minimum viable product with core functionality. | Backend development, API integration, frontend implementation. | 5 developers, 1 QA engineer. | 10 | Not Started
Testing & Validation | Conduct user testing and performance optimization.Beta release, bug fixing, feedback collection. | 1 QA lead, 2 testers, 1 DevOps engineer. | 5 | Not Started
Launch & Go-to-Market | Publish product and initiate marketing campaign. | Launch event, social media rollout, partner onboarding. | 1 Marketing lead, 2 content creators, 1 sales rep. | 3 | Planned