## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Status | Dependencies | Resource Allocation
Project Initiation | Jane Smith | 2024-03-01 | 2024-03-10 | 10 | Planned | - | Project Manager, Finance Lead
Requirements Gathering | Alex Chen | 2024-03-11 | 2024-03-25 | 15 | In Progress | Project Initiation | Business Analysts, Stakeholders
Design Phase | Samira Patel | 2024-03-26 | 2024-04-15 | 20 | Planned | Requirements Gathering | UI/UX Designer, Technical Lead
Development Phase | Jordan Lee | 2024-04-16 | 2024-05-31 | 46 | Not Started | Design Phase | Full Development Team
Testing & Quality Assurance | Morgan Wright | 2024-06-01 | 2024-06-15 | 15 | Planned | Development Phase | QA Engineers, Test Managers
Deployment & Launch | Taylor Reed | 2024-06-16 | 2024-06-18 | 3 | Not Started | Testing & QA | IT Operations, DevOps Team
Post-Launch Review | Jane Smith | 2024-06-19 | 2024-06-21 | 3 | Planned | Deployment & Launch | Project Manager, Customer Support