## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Resource Required | Priority | Status | Dependencies
PRJ-001 | Project Initiation Phase | John Smith | 2024-03-01 | 2024-03-15 | 15 | Project Manager, Stakeholders | High | In Progress | None
PRJ-002 | <Requirements Gathering | Sarah Lee | 2024-03-16 | 2024-04-10 | 35 | Business Analysts, Clients | High | Planned | PRJ-001
PRJ-003 | Design & Prototyping | Michael Chen | 2024-04-11 | 2024-05-15 | 35 | UI/UX Designers, Developers | Medium | Not Started | PRJ-002
PRJ-004 | Development Phase | Lisa Wong | 2024-05-16 | 2024-07-31 | 86 | Software Developers, QA Team | High | Not Started | PRJ-003
PRJ-005 | Testing & QA | David Kim | 2024-08-01 | 2024-08-31 | 31 | QA Engineers, Testers | High | Planned | PRJ-004
PRJ-006 | Deployment & Training | Emma Taylor | 2024-09-01 | 2024-09-30 | 30 | IT Ops, Training Staff | Medium | Not Started | PRJ-005
Template Version – Resource Planning ¦ Project Plan