## Worksheet
Task | Responsible | Start Date | End Date | Status | Progress (%) | Resources Required | Dependencies | Priority
Project Initiation | John Doe | 2024-01-01 | 2024-01-15 | Completed | 100% | Project Manager, Stakeholders | - | High
Requirements Gathering | Jane Smith | 2024-01-16 | 2024-02-15 | In Progress | 65% | Business Analysts, Clients | Project Initiation | High
Design Phase | Mike Johnson | 2024-02-16 | 2024-03-31 | Not Started | 0% | UI/UX Designers, Developers | Requirements Gathering | Medium
Development Phase | Sarah Lee | 2024-04-01 | 2024-06-30 | Not Started | 0% | Software Developers, QA Team | Design Phase | High
Testing & Validation | David Kim | 2024-07-01 | 2024-08-15 | Not Started | 0% | QA Engineers, Test Managers | Development Phase | High
Deployment & Training | Lisa Wong | 2024-08-16 | 2024-09-30 | Not Started | 0% | IT Team, End Users | Testing & Validation | Medium