## Worksheet
Week | Project Phase | Resource Assigned | Task Description | Start Date | End Date | Status | Progress (%) | Dependencies | Notes
1 | Initiation | Project Manager, Business Analyst | Define project scope and objectives | 2024-04-01 | 2024-04-07 | Completed | 100% | - | Approved by stakeholders
2 | Planning | Project Manager, Team Lead | Develop project timeline and budget | 2024-04-08 | 2024-04-14 | In Progress | 75% | Phase 1 completion | Review with finance team pending approval
3 | Execution | Development Team, QA Lead | Develop core application modules | 2024-04-15 | 2024-04-21 | Not Started | 0% | Phase 2 planning complete | Team onboarding scheduled for week 4
4 | Execution | Development Team, QA Lead | Test core modules and fix bugs | 2024-04-22 | 2024-04-28 | Planned | 30% | Module development complete | Bug tracking in JIRA updated weekly
5 | Review & Adjustment | Project Manager, Stakeholders | Conduct mid-project review and adjust plan | 2024-04-29 | 2024-05-05 | Scheduled | - | Execution phase 1 complete | Adjustments to scope approved