## Worksheet
Resource | Task | Duration (Weeks) | Assigned Team | Start Date | End Date | Status | Capacity Utilization | Dependencies | Budget Allocation ($)
Project Manager | Initiate Project Planning | 2 | PM Team | 2024-06-01 | 2024-06-02 | On Track | 85% | None | 20,000
IT Specialist | System Requirements Gathering | 4 | IT Team | 2024-06-03 | 2024-06-06 | In Progress | 90% | Project Initiation | 25,000
Marketing Lead | Market Analysis & Strategy | 3 | Marketing Team | 2024-06-04 | 2024-06-06 | Completed | 95% | None | 18,000
Finance Officer | Budget Finalization | 2 | Finance Team | 2024-06-05 | 2024-06-06 | Approved | 100% | Market Analysis | 22,000
Operations Manager | Resource Allocation Plan | 5 | Operations Team | 2024-06-07 | 2024-06-11 | Scheduled | 80% | System Requirements | 30,000