## Worksheet
Task | Description | Responsible Person | Start Date | End Date | Status | Resources Required th>
Project Initiation | Define project scope, objectives, and key stakeholders. | Jane Doe | 2023-10-01 | 2023-10-15 | Completed | Project Manager, Stakeholder Analysis Team
Resource Allocation | Determine staffing and equipment needs for each phase. | John Smith | 2023-10-16 | 2023-10-30 | In Progress | HR Team, IT Department, Finance Office
Phase 1 Development | Build core product functionality based on design specs. | Alice Brown | 2023-11-01 | 2023-11-20 | Pending | Development Team, QA Engineers
Testing & Validation | Conduct unit, integration, and user acceptance testing. | Mike Taylor | 2023-11-21 | 2023-12-05 | Not Started | QA Team, UX Designers
Deployment & Launch | Publish the solution to production environment. | Sarah Lee | 2023-12-06 | 2023-12-15 | Planned | IT Operations, Support Staff