## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Resource Required | Budget (USD) | Status | Dependencies
TP-001 | Project Initiation & Planning | Jane Smith | 2024-03-15 | 2024-03-31 | Project Manager, Business Analyst | 15,000 | In Progress | None
TP-002 | Requirement Gathering Workshop | Mark Johnson
TP-003 | Design Phase - UI/UX | Lena Chen | 2024-04-15 | 2024-05-10 | UI/UX Designer, Product Owner | 8,500 | Pending Approval | TP-002
TP-004 | Development Sprint 1 | David Kim | 2024-05-11 | 2024-06-15 | Software Engineers (x3) | 30,000 | Not Started | TP-003
TP-005 | Testing & Quality Assurance | Sarah Lee | 2024-06-16 | 2024-07-10 | QA Engineers (x2) | 12,000 | Planned | TP-004
TP-006 | Deployment & Go-Live | Tim Brown | 2024-07-11 | 2024-07-18 | DevOps Team, Operations Manager | 5,000 | Not Started | TP-005