## Worksheet
Project Phase | Start Date | End Date | Responsible Team | Key Deliverables | Resource Allocation | Milestone Status | Dependencies
Initiation | 2024-01-15 | 2024-01-31 | Project Office | Feasibility Report, Stakeholder Analysis | 3 FTEs | Completed | None
Planning | 2024-02-01 | 2024-03-15 | Project Management Team | WBS, Risk Register, Budget Plan | 5 FTEs | In Progress | Initiation Phase
Execution | 2024-04-01 | 2024-08-31 | Engineering & Operations Teams | System Development, Training Modules | 10 FTEs | Planned | Planning Phase, Procurement
Monitoring & Control | 2024-09-01 | 2024-11-30 | Project Controls Unit | Performance Reports, Change Logs | 4 FTEs | Scheduled | Execution Phase, Testing Phase
Closure | 2024-12-01 | 2024-12-31 | Project Office & Stakeholders | Final Report, Lessons Learned | 2 FTEs | Pending | Monitoring & Control Phase