## Worksheet
Month | Project Phase | Key Activities | Responsible Team | Milestone Date | Resource Allocation | Budget (USD)
January | Planning & Initiation | Scope definition, stakeholder alignment, risk assessment | Project Office & Strategy Team | Jan 31, 2024 | 10 FTEs (Full-time equivalents) | $50,000
February | Resource Mapping | Workforce inventory, skill gap analysis, procurement planning | HR & Operations Team | Feb 28, 2024 | 8 FTEs + 3 contractors | $45,000
March | Project Design & Scheduling | Develop project schedule, WBS finalization, timeline validation | Project Management Office | Mar 30, 2024 | 12 FTEs (core team) | $60,000
April | Resource Assignment & Training | Assign personnel, initiate training programs, tool setup | Training & Onboarding Team | Apr 25, 2024 | 10 FTEs + 5 trainers | $40,000
May | Execution Phase Start | Commence core project activities, progress tracking setup | All Project Teams | May 15, 2024 | 15 FTEs (active) | $75,000
June | Mid-Year Review & Adjustment | Performance review, resource reallocation, risk mitigation | Project Steering Committee | Jun 30, 2024 | 9 FTEs (revised) | $55,000
July | Key Delivery & Quality Assurance | Deliver core outputs, conduct internal audits | Quality & Delivery Team | Jul 20, 2024 | 14 FTEs (focused) | $80,000
August | Stakeholder Feedback & Iteration | Collect feedback, adjust deliverables, refine processes | User Engagement Team | Aug 28, 2024 | 11 FTEs (feedback loop) | $35,000
September | Final Testing & Validation | System validation, compliance checks, final sign-off | QA & Compliance Team | Sep 30, 2024 | 10 FTEs (testing) | $50,000
October | Go-Live & Deployment | Deploy project to production, user onboarding | Operations & IT Team | Oct 15, 2024 | 13 FTEs (deployment) | $65,000
November | Post-Go-Live Support & Review | Monitor performance, provide support, conduct closure review | Support & Finance Team | Nov 20, 2024 | 8 FTEs (support) | $30,000
December | Project Closure & Reporting | Final reporting, budget reconciliation, lessons learned | Project Office & Finance Team | Dec 31, 2024 | 6 FTEs (closure) | $25,000