## Worksheet
Task | Start Date | End Date | Responsible Party | Resource Allocation | Status | Dependencies
Project Initiation | 2024-01-15 | 2024-01-25 | Project Manager | 1 Full-Time | Completed | None
Feasibility Study | 2024-01-26 | 2024-02-10 | Business Analysts | 3 Part-Time | In Progress | Project Initiation
Requirements Gathering | 2024-02-11 | 2024-03-15 | Stakeholders & Team | 5 Full-Time | Planned | Feasibility Study
Design Phase | 2024-03-16 | 2024-04-30 | UX & IT Designers | 4 Full-Time | Not Started | Requirements Gathering
Development & Testing | 2024-05-01 | 2024-07-31 | Software Development Team | 8 Full-Time | Planned | Design Phase
User Training & Deployment | 2024-08-01 | 2024-08-31 | Training Officers & IT Staff | 3 Full-Time | Not Started | Development & Testing
Post-Implementation Review | 2024-09-01 | 2024-09-15 | Project Manager & Stakeholders | 2 Full-Time | Planned | User Training & Deployment