## Worksheet
Project Phase | Start Date | End Date | Responsible Team | Key Deliverables | Status
Requirement Gathering | 2024-03-01 | 2024-03-15 | Client Engagement Team | Scope document, User stories | On Track
Design & Prototyping | 2024-03-16 | 2024-04-10 | Design & UX Team | Wireframes, UI mockups | In Progress
Development Phase | 2024-04-11 | 2024-06-30 | Engineering Team | Core functionality, API integration | Planned
Testing & QA | 2024-07-01 | 2024-07-31 | QA & Compliance Team | Bug reports, Performance testing | Pending
Deployment & Launch | 2024-08-01 | 2024-08-15 | Operations & Client Team | Live system, User training materials | Not Started