## Worksheet
Phase | Start Date | End Date | Responsible Team | Status | Resource Allocation
Initiation | 2024-03-01 | 2024-03-15 | Project Office | Completed | 1 FTE, 5 Days
Planning | 2024-03-16 | 2024-04-30 | Strategy Team | In Progress | 2 FTEs, 6 Weeks
Design & Development | 2024-05-01 | 2024-07-31 | Engineering Team | Pending Approval | 3 FTEs, 9 Weeks
Testing & Validation | 2024-08-01 | 2024-09-15 | QA & DevOps | Not Started | 1.5 FTEs, 6 Weeks
Deployment & Handover | 2024-10-01 | 2024-10-31 | Operations Team | Planned | 1 FTE, 4 Weeks