## Worksheet
Task | Start Date | End Date | Responsible Party | Status | Resource Allocation
Project Initiation | 2024-01-01 | 2024-01-15 | Project Manager | Completed | 1 Full-Time
Requirements Gathering | 2024-01-16 | 2024-02-15 | Business Analysts | In Progress | 2 Full-Time
Design Phase | 2024-02-16 | 2024-03-31 | UX/UI Design Team | Planned | 3 Full-Time
Development Phase | 2024-04-01 | 2024-06-30 | Software Developers | Not Started | 5 Full-Time
Testing & Quality Assurance | 2024-07-01 | 2024-08-15 | QA Team | Not Started | 2 Full-Time
Deployment & Go-Live | 2024-08-16 | 2024-08-31 | IT Operations Team | Not Started | 3 Full-Time
Post-Implementation Review | 2024-09-01 | 2024-09-30 | Project Manager & Stakeholders | Not Started | 1 Full-Time