## Worksheet
Task | Start Date | End Date | Responsible Party | Status | Dependencies | Resources Required
Project Initiation | 2024-03-01 | 2024-03-15 | Project Manager | In Progress | - | Budget Approval, Stakeholder Meeting
Requirements Gathering | 2024-03-16 | 2024-04-10 | Business Analysts | Planned | Project Initiation Completed | Stakeholders, Interviews, Workshops
Design Phase | 2024-04-11 | 2024-05-31 | UX & UI Team | Not Started | Requirements Finalized | Design Tools, Sketching Equipment
Development Phase | 2024-06-01 | 2024-08-31 | Software Developers | Planned | Design Phase Complete | Servers, Coding Environment, Dev Tools
Testing & Quality Assurance | 2024-09-01 | 2024-10-15 | QA Team | Not Started | Development Complete | Test Cases, Automation Tools, Bug Tracking System
Deployment & Go-Live | 2024-10-16 | 2024-10-30 | IT Operations Team | Planned | Testing Phase Complete | Production Servers, Backup Systems, Admin Access
Post-Deployment Review & Optimization | 2024-11-01 | 2024-11-30 | Project Manager & Team | Not Started | Go-Live Completed | User Feedback, Performance Metrics, Reporting Tools