## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Resource Allocation | Dependencies | Status | Milestones | Budget (USD) | Progress (%)
PRJ-001 | Project Initiation & Feasibility Study | 2024-03-15 | 2024-03-31 | 16 | Alice Johnson | PMO, Finance Team |  | On Track | Initiation Complete | $15,000 | 100%
PRJ-002 | Requirements Gathering & Analysis | 2024-04-01 | 2024-05-15 | 65 | Bob Smith | Product & UX Team | PRJ-001 | In Progress |  | $45,000 | 65%
PRJ-003 | System Design & Architecture | 2024-05-16 | 2024-06-30 | 55 | Carol Lee | Engineering Team | PRJ-002 | Planned |  | $75,000 | 0%
PRJ-004 | Development & Coding Phase | 2024-07-01 | 2024-09-30 | 90 | David Kim | Backend & Frontend Teams | PRJ-003 | Not Started |  | $200,000 | 0%
PRJ-005 | Testing & Quality Assurance | 2024-10-01 | 2024-11-30 | 60 | Eve Brown | QA Team, DevOps | PRJ-004 | Planned |  | $50,000 | 0%
PRJ-006 | Deployment & Go-Live | 2024-12-01 | 2024-12-15 | 15 | Frank White | Operations & Support Team | PRJ-005 | Not Started |  | $30,000 | 0%