## Worksheet
Task ID | Project Phase | Start Date | End Date | Budget (USD) | Allocated Resources | Status | Reserve (%)
PRJ-001 | Initiation | 2024-03-01 | 2024-03-15 | 50,000 | Project Manager, Finance Lead | On Track | 5%
PRJ-002 | Planning | 2024-03-16 | 2024-05-31 | 120,000 | Operations Team, IT Analysts | On Track | 3%
PRJ-003 | Execution | 2024-06-01 | 2024-11-30 | 750,000 | Development Team, QA Engineers | At Risk | 10%
PRJ-004 | Review & Close | 2024-12-01 | 2025-01-31 | 80,000 | Finance Team, Compliance Officer | On Track | 2%