## Worksheet
Task | Start Date | End Date | Responsible Party | Duration (Days) | Status | Dependencies
Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | Freelancer A | 1 | Completed | -
Resource Requirements Analysis | 2024-03-16 | 2024-03-20 | Freelancer B | 5 | In Progress | Project Kickoff Meeting
Team Assignment & Role Definition | 2024-03-21 | 2024-03-25 | Freelancer C | 5 | Planned | Resource Requirements Analysis
Budget & Funding Forecasting | 2024-03-26 | 2024-03-31 | Freelancer D | 6 | Pending | Team Assignment & Role Definition
Risk Assessment & Mitigation Plan | 2024-04-01 | 2024-04-05 | Freelancer E | 5 | Scheduled | Budget & Funding Forecasting
Final Resource Planning Review | 2024-04-06 | 2024-04-07 | Project Manager | 2 | Scheduled | Risk Assessment & Mitigation Plan