## Worksheet
Month | Project Phase | Key Activities | Responsible Team | Start Date | End Date | Status | Resources Required
January | Initiation & Feasibility Study | Stakeholder interviews, Scope definition, Risk assessment | Project Office & Business Analysis Team | 2024-01-01 | 2024-01-31 | On Track | Business Analysts, 3 IT Consultants
February | Requirements Gathering | Requirement workshops, Document finalization, Approval process | Requirements Team & Client Reps | 2024-02-01 | 2024-02-28 | On Track | Requirements Analysts, 1 Project Manager
March | Design & Prototyping | System architecture design, UI/UX mockups, Technical validation | Design Team & Engineering Lead | 2024-03-01 | 2024-03-31 | On Track | UI/UX Designers, 2 Engineers
April | Development (Phase 1) | Core module development, API integration, Unit testing | Engineering Team | 2024-04-01 | 2024-04-30 | On Track | 6 Developers, QA Lead
May | Development (Phase 2) | Feature implementation, Integration testing, Performance tuning | Engineering Team & QA Team | 2024-05-01 | 2024-05-31 | On Track | 6 Developers, 3 QA Engineers
June | UAT & Final Testing | User acceptance testing, Bug resolution, Final sign-off | Client Team & QA Team | 2024-06-01 | 2024-06-30 | On Track | QA Team, Client Representatives
July | Deployment & Go-Live | Production deployment, Change management, Training rollout | IT Operations & Training Team | 2024-07-01 | 2024-07-31 | On Track | Operations Team, 5 Trainers