## Worksheet
Project Phase | Start Date | End Date | Responsible Team | Key Deliverables | Status
Initiation | 01/01/2024 | 03/15/2024 | Project Office | Feasibility Study, Stakeholder Analysis, Project Charter | Completed
Planning | 03/16/2024 | 06/30/2024 | Operations & Strategy Team | Work Breakdown Structure, Risk Register, Budget Plan | In Progress
Execution | 07/01/2024 | 10/31/2024 | Engineering & Delivery Team | System Development, Testing, Training Modules | Pending Start
Monitoring & Control | 11/01/2024 | 01/31/2025 | Project Management Office | Performance Reviews, Change Logs, Issue Tracking | Not Started
Closure | 02/01/2025 | 03/31/2025 | Project Office & Client Team | Final Report, Lessons Learned, Sign-off Documentation | Not Started