## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Dependencies
Project Initiation | 2024-03-01 | 2024-03-15 | John Smith | Completed | None
Resource Assessment | 2024-03-16 | 2024-03-31 | Maria Lopez | In Progress | Project Initiation
Budget Planning | 2024-04-01 | 2024-04-15 | David Chen | Not Started | Resource Assessment
Risk Analysis | 2024-04-16 | 2024-05-05 | Sarah Williams | Planned | Budget Planning
Execution Phase Start | 2024-05-06 | 2024-07-31 | Team Lead Group | Not Started | Risk Analysis