## Worksheet
Task | Start Date | End Date | Responsible Party | Status | Resource Allocation
Project Initiation | 2024-03-01 | 2024-03-15 | Project Manager | On Track | 1 Full-Time
Requirements Gathering | 2024-03-16 | 2024-04-10 | Business Analysts | On Track | 2 Full-Time
Design Phase | 2024-04-11 | 2024-05-30 | UI/UX Team | On Track | 3 Full-Time
Development Phase | 2024-06-01 | 2024-08-31 | Development Team | On Track | 6 Full-Time
Testing & Quality Assurance | 2024-09-01 | 2024-10-15 | QA Engineers | On Track | 3 Full-Time
Deployment & Go-Live | 2024-10-16 | 2024-10-30 | IT Operations | On Track | 2 Full-Time
Post-Implementation Review | 2024-11-01 | 2024-11-30 | Project Manager | On Track | 1 Full-Time