## Worksheet
Task | Start Date | End Date | Responsible | Status | Dependencies
Project Initiation | 2024-01-01 | 2024-01-15 | John Smith | Completed
Resource Assessment | 2024-01-16 | 2024-02-05 | Sarah Lee | In Progress | Project Initiation
Scope Definition | 2024-02-06 | 2024-03-15 | Marcus Brown | Pending | Resource Assessment
Team Allocation | 2024-03-16 | 2024-04-10 | Linda Wong | Not Started | Scope Definition
Execution Planning | 2024-04-11 | 2024-05-31 | David Kim | Pending | Team Allocation
Phase Review & Adjustments | 2024-06-01 | 2024-06-15 | All Team Members | Not Started | Execution Planning