## Worksheet
Project Phase | Start Date | End Date | Responsible Team | Key Deliverables | Budget (USD) | Status
Initiation | 01/04/2024 | 05/04/2024 | Project Office | Feasibility Study, Project Charter | $50,000 | Completed
Planning | 06/04/2024 | 15/06/2024 | Project Management Team | Scope Document, Risk Register, WBS | $80,000 | In Progress
Execution | 16/06/2024 | 30/09/2024 | Development Team | Functional Modules, User Acceptance Testing | $400,000 | Scheduled
Monitoring & Control | 01/10/2024 | 30/11/2024 | Operations & Quality Team | Performance Reports, Change Logs | $50,000 | Planned
Closure | 01/12/2024 | 05/12/2024 | Project Steering Committee | Final Report, Lessons Learned | $20,000 | Pending