## Worksheet
Activity | Start Date | End Date | Responsible | Status | Dependencies
Market Research | 2024-03-01 | 2024-03-15 | Marketing Team | Completed | None
Product Design | 2024-03-16 | 2024-04-10 | Design Team | In Progress | Market Research
Development Phase | 2024-04-11 | 2024-06-30 | Engineering Team | Not Started | Product Design
User Testing | 2024-07-01 | 2024-07-31 | Quality Assurance | Not Started | Development Phase
Launch Preparation | 2024-08-01 | 2024-08-31 | Operations Team | Not Started | User Testing