## Worksheet
Task | Start Date | End Date | Responsible Team Member | Status | Dependencies | Notes / Remarks
Project Initiation & Planning | 2024-03-01 | 2024-03-15 | Project Management Team | In Progress | - | Finalize scope, budget, and key deliverables.
Resource Allocation & Team Assignment | 2024-03-16 | 2024-03-25 | HR & Operations Team | Not Started | Project Initiation Complete | Assign roles and define workloads.
Risk Assessment & Mitigation Plan | 2024-03-26 | 2024-04-05 | Risk Management Team | Not Started | Resource Allocation Complete | Identify potential risks and create response strategies.
Phase 1 Development & Testing | 2024-04-06 | 2024-05-15 | Engineering & QA Teams | Not Started | Risk Assessment Complete | Build core features and conduct initial testing.
Stakeholder Review & Feedback Session | 2024-05-16 | 2024-05-23 | Client & Product Teams | Not Started | Phase 1 Testing Complete | Gather feedback and adjust scope if needed.
Phase 2 Development & Integration | 2024-05-24 | 2024-07-10 | Engineering & Integration Team | Not Started | Stakeholder Feedback Received | Integrate features and prepare for go-live.
Final Testing & UAT (User Acceptance Testing) | 2024-07-11 | 2024-07-30 | QA & Client Teams | Not Started | Phase 2 Development Complete | Validate functionality with end users.
Go-Live & Post-Implementation Support | 2024-08-01 | 2024-08-31 | Support & Operations Team | Not Started | UAT Complete | Deploy solution and provide 30-day support.