## Worksheet
Task ID | Task Name | Start Date | End Date | Responsible Person | Resource Required | Status | Dependencies
PRJ-001 | Project Initiation & Planning | 2024-03-01 | 2024-03-15 | Jane Smith | Project Manager, Stakeholder Analysis Team | On Track | None
PRJ-002 | Resource Assessment & Allocation | 2024-03-16 | 2024-04-10 | John Doe | HR, Budget Analyst, IT Team | In Progress | PRJ-001
PRJ-003 | Scope & Timeline Finalization | 2024-04-11 | 2024-04-25 | Sarah Lee | Project Manager, Legal Reviewer | Pending Approval | PRJ-002
PRJ-004 | Team Training & Onboarding | 2024-05-01 | 2024-05-15 | Michael Brown | Training Coordinator, Department Heads | Not Started | PRJ-003
PRJ-005 | Phase 1 Development Launch | 2024-06-01 | 2024-07-31 | Linda Green | Development Team, QA Team | Planned | PRJ-004
Template Version: v2.1 – Resource Planning Project Timeline