## Worksheet
Task | Start Date | End Date | Assigned To | Status | Progress % | Dependencies
Project Initiation | 2024-01-15 | 2024-01-25 | John Smith | Completed | 100%
Resource Assessment | 2024-01-26 | 2024-02-10 | Sarah Lee | In Progress | 75% | Project Initiation
Budget Planning | 2024-02-11 | 2024-03-01 | Mike Chen | Not Started | 0% | Resource Assessment
Risk Analysis | 2024-03-02 | 2024-03-15 | Lisa Park | Planned | 0% | Budget Planning
Team Training | 2024-03-16 | 2024-04-05 | David Kim | Not Started | 0% | Risk Analysis