## Worksheet
Week | Project Phase | Key Activities | Responsible Team | Start Date | End Date | Status | Resource Allocation
1 | Initiation & Planning | Feasibility Study, Scope Definition | Project Management Office | 2023-10-01 | 2023-10-07 | In Progress | 5 Full-Time Equivalents (FTEs)
2 | Design & Requirements | System Architecture, User Needs Gathering | Engineering & UX Team | 2023-10-08 | 2023-10-14 | Pending Review | 6 FTEs (including consultants)
3 | Development Phase (Sprint 1) | Core Module Development, API Integration | Development Team | 2023-10-15 | 2023-10-21 | In Progress | 8 FTEs (distributed across teams)
4 | Development Phase (Sprint 2) | User Interface Finalization, Testing Setup | Frontend & QA Teams | 2023-10-22 | 2023-10-28 | Scheduled | 7 FTEs (QA + UX)
5 | Testing & Validation | System Testing, User Acceptance Testing (UAT)QA & Client Stakeholders | 2023-10-29 | 2023-11-04 | Pending Approval | 6 FTEs (QA, Support)
6 | Deployment Preparation | Environment Setup, Rollout Plan Finalization | Operations & IT Security | 2023-11-05 | 2023-11-11 | In Progress | 4 FTEs (IT Ops + Security)
7 | Go-Live & Post-Deployment Support | Live Deployment, Monitoring & Incident Response | Support Team & Project Manager | 2023-11-12 | 2023-11-18 | Scheduled | 5 FTEs (Support + PM)