## Worksheet
Project ID | Project Name | Start Date | End Date | Budget (USD) | Current Status | Responsible Team | Resource Allocation | Milestones | Dependencies | Risk Assessment | Approved By | Next Review Date
PRJ-2024-001 | Cloud Migration Initiative | 2024-03-15 | 2024-07-30 | $150,000 | On Track | IT Operations Team | 5 Developers, 2 DevOps, 1 Security Lead | Phase 1 Complete; Phase 2 in Progress | Data Backup System Completion | Medium - Data Integrity Risk | John Smith (CTO) | 2024-06-15
PRJ-2024-002 | Customer Experience Platform Upgrade | 2024-04-01 | 2024-11-30 | $325,000 | Planning Phase | Product & UX Team | 3 UX Designers, 4 Backend Engineers | User Testing, UI/UX Prototyping | Approval of Budget and Vendor Contracts | Low - Timeline Delay Risk | Lisa Chen (Product Director) | 2024-05-15
PRJ-2024-003 | Supply Chain Optimization Project | 2024-05-10 | 2024-12-31 | $475,000 | In Progress | Logistics & Operations Team | 12 Analysts, 3 Logistics Managers | Vendor Audit, Route Optimization Model | ERP System Integration Completion | High - Vendor Performance Risk | Michael Reed (Operations VP) | 2024-08-15