## Worksheet
Project ID | Project Name | Client | Start Date | End Date | Status | Budget (USD) | Assigned Freelancer | Progress (%) | Next Milestone
PRJ-2024-001 | Website Redesign for TechStart Inc. | TechStart Inc. | 2024-03-15 | 2024-05-30 | In Progress | 15,000 | Alex Rivera | 65% | Launch Responsive Design Phase
PRJ-2024-002 | Mobile App Development – FitLife App | FitLife Health Co. | 2024-04-01 | 2024-07-15 | Planning | 35,000 | Jordan Lee | 20% | Define UI/UX Requirements
PRJ-2024-003 | Social Media Strategy – EcoBrand | EcoBrand Solutions | 2024-03-28 | 2024-06-15 | On Track | 8,500 | Mia Chen | 90% | Final Content Review
PRJ-2024-004 | Content Creation for Startup Hub | Startup Hub Network | 2024-03-18 | 2024-05-31 | Delayed | 6,200 | Sam Patel | 45% | Reschedule Content Production