## Worksheet
Project ID | Project Name | Department | Start Date | End Date | Budget (USD) | Current Status | Primary Resource | Resource Allocation | Milestone Due Date | Risk Level
PRJ-2024-001 | Cloud Migration Initiative | IT Operations | 2024-03-01 | 2024-06-30 | $580,000 | On Track | John A. Rivera | 3 full-time engineers, 2 consultants | 2024-05-15 | Medium
PRJ-2024-002 | Customer Experience Platform Launch | Marketing & Product | 2024-04-10 | 2024-09-30 | $750,000 | In Progress | Sarah T. Chen | 4 developers, 3 UX designers | 2024-07-31 | High
PRJ-2024-003 | Supply Chain Optimization | Logistics & Procurement | 2024-05-05 | 2024-11-30 | $920,000 | Planning Phase | Michael L. Wright | 5 analysts, 2 operations managers | 2024-08-05 | Medium
PRJ-2024-004 | AI-Powered Sales Analytics | Data Science & Sales | 2024-06-01 | 2024-12-31 | $850,000 | Approved, Pending Funding | Dr. Emily R. Foster | 3 data scientists, 1 ML engineer | 2024-09-15 | High
PRJ-2024-005 | Global Expansion Strategy | International Operations | 2024-07-15 | 2025-03-31 | $1.8M | Proposal Review | David K. Patel | 6 strategists, 3 regional leads | 2024-10-01 | Critical