## Worksheet
Project Name | Team Member | Task Description | Assigned Date | Due Date | Status | Progress (%) | Resource Required | Dependencies | Notes
Website Redesign | Jane Doe | Update homepage layout and navigation | 2023-10-03 | 2023-10-17 | In Progress | 65% | Design Team, Web Developer | Content approval pending
Mobile App Development | John Smith | Develop user authentication module | 2023-10-04 | 2023-10-25 | Not Started | 0% | Backend Dev, QA Tester | Database schema finalized
Marketing Campaign Launch | Lisa Chen | Execute social media rollout | 2023-10-05 | 2023-10-15 | On Track | 90% | Content Creator, Marketing Manager | Budget approved | Target audience engagement high
Server Migration | Mike Brown | Migrate legacy systems to cloud platform | 2023-10-06 | 2023-10-30 | Planning | 25% | DevOps Team, Cloud Engineer | Security audit complete