## Worksheet
Task ID | Task Name | Resource Required | Start Date | End Date | Duration (Days) | Assigned To | Status | Priority | Dependencies
RPL-001 | System Infrastructure Setup | Network Engineers, IT Admins | 2024-04-01 | 2024-04-15 | 15 | John Doe | In Progress | High | None
RPL-002 | Develop Core Application Modules | Software Developers, QA Team | 2024-04-16 | 2024-05-31 | 46 | Sarah Lee | Planned | High | RPL-001
RPL-003 | Database Migration & Testing | DBA Team, Test Analysts | 2024-06-01 | 2024-06-15 | 15 | Mike Chen | Pending Approval | Medium | RPL-002
RPL-004 | User Training & Onboarding | Training Officers, HR | 2024-07-01 | 2024-07-15 | 15 | Lisa Park | Scheduled | Low | RPL-003
RPL-005 | Final System Integration & Go-Live | All Teams | 2024-08-01 | 2024-08-15 | 15 | David Kim | Not Started | High | RPL-002, RPL-003