## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Resources Needed
Project Initiation | 2024-03-01 | 2024-03-10 | John Smith | Completed | Project Manager, Budget Plan
Requirement Gathering | 2024-03-11 | 2024-03-25 | Sarah Lee | In Progress | Stakeholders, Interviews
Design Phase | 2024-03-26 | 2024-04-15 | Mike Chen | Planned | Design Team, Tools
Development Phase | 2024-04-16 | 2024-05-30 | Lisa Wang | Not Started | Developers, Servers
Testing & QA | 2024-06-01 | 2024-06-20 | Robert Kim | Planned | QA Team, Test Environment
Deployment | 2024-06-21 | 2024-06-30 | James Taylor | Not Started | IT Ops, Cloud Platform