## Worksheet
Project Name | Resource | Start Date | End Date | Duration (Days) | Assigned To | Status | Priority | Notes
Q4 Marketing Campaign | Design Team | 2023-10-01 | 2023-10-30 | 30 | Sarah Johnson | On Track | High | Final designs to be approved by client by Oct. 25.
New Product Launch | Engineering Team | 2023-10-05 | 2023-11-05 | 40 | Mike Chen | In Progress | Critical | Prototype testing delayed by supply chain issue.
Customer Onboarding Program | Operations Team | 2023-10-15 | 2023-11-30 | 65 | Lisa Wang | Planned | Medium | Training materials to be finalized by Oct. 30.
IT Infrastructure Upgrade | IT Department | 2023-10-20 | 2023-11-15 | 46 | David Kim | Approved | High | Backup systems to be tested during off-peak hours.