## Worksheet
Task ID | Task Name | Responsible | Start Date | End Date | Status | Resources Required th>
#001 | Project Initiation | Jane Smith | 2024-03-01 | 2024-03-15 | Completed | Project Manager, Analysts (2)
#002 | Requirement Gathering | Mike Johnson | 2024-03-16 | 2024-04-10 | In Progress | Business Analysts (3)
#003 | Design Phase | Sarah Lee | 2024-04-11 | 2024-05-05 | Pending Approval | UX Designer, Developers (4)
#004 | Development Build | Tony Brown | 2024-05-06 | 2024-06-15 | Not Started | Full Development Team (8)
#005 | Testing & QA | Lisa Chen | 2024-06-16 | 2024-07-10 | Scheduled | QA Engineers (5)
#006 | Deployment Plan | David Wong | 2024-07-11 | 2024-07-31 | Planning Phase | Ops Team, DevOps (3)