## Worksheet
Project | Resource | Task | Start Date | End Date | Status | Assigned To | Capacity (hrs/wk) | Progress %
Product Launch Q4 | Marketing Team | Campaign Design | 2023-10-01 | 2023-10-30 | In Progress | Anna Lee | 40 | 65%
Product Launch Q4 | Engineering Team | App Development | 2023-09-15 | 2023-11-15 | On Track | David Kim | 50 | 80%
Customer Support Upgrade | Support Team | System Integration | 2023-10-05 | 2023-11-30 | Planned | Sara Patel | 35 | 0%
Digital Transformation | IT Department | Infrastructure Audit | 2023-09-01 | 2023-10-31 | Completed | James Wong | 45 | 100%
Global Expansion | Operations Team | Market Research | 2023-10-15 | 2023-12-30 | Pending | Lena Thomas | 40 | 0%