## Worksheet
Task ID | Task Name | Responsible Party | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies | Notes
T001 | Project Kickoff Meeting | Project Manager | 2024-03-15 | 2024-03-15 | 1 | Completed | High |  | Finalize project goals and team assignments.
T002 | <Resource Requirements Analysis | Resource Planner | 2024-03-16 | 2024-03-18 | 3 | In Progress | Medium | T001 | Identify staffing needs and budget constraints.
T003 | Team Training Sessions | Training Coordinator | 2024-03-20 | 2024-03-25 | 6 | Planned | High | T002 | Ensure all team members are trained on new tools.
T004 | Procurement of Equipment | Purchasing Manager | 2024-03-26 | 2024-04-05 | 10 | Pending | High |  | Finalize vendor agreements and delivery timelines.
T005 | Project Review & Adjustments | Project Manager | 2024-04-10 | 2024-04-11 | 2 | Planned | Medium | T003, T004 | Assess progress and adjust resource allocation if needed.