## Worksheet
Task | Start Date | End Date | Assigned To | Status | Priority | Resources Needed
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | Jane Smith | Completed | Low | Meeting Room, Chair, Project Doc
Requirements Gathering | 2024-04-02 | 2024-04-10 | Mark Johnson | In Progress | Medium | Stakeholders, Research Tools, Notes
Design Phase Final Review | 2024-04-15 | 2024-04-18 | Sarah Lee | Pending | High | Design Team, Feedback Form, Screenshots
Development Phase Start | 2024-04-20 | 2024-05-31 | Team A (All Members) | Planned | High | Servers, Codebase, Dev Tools
Testing and Quality Assurance | 2024-06-01 | 2024-06-15 | David Chen | Scheduled | Medium | Test Environment, QA Tools, Reports