## Worksheet
Project | Task | Start Date | End Date | Responsible Party | Status | Notes
Website Redesign | Wireframe Design | 2024-03-15 | 2024-03-25 | Anna Lopez | In Progress | Final design approved by client.
Website Redesign | Front-End Development | 2024-03-26 | 2024-04-10 | David Chen | On Hold | Waiting on backend API integration.
Marketing Campaign | Social Media Strategy | 2024-03-10 | 2024-03-31 | Sarah Kim | Completed | Content calendar published.
Client Onboarding | Initial Meeting | 2024-03-05 | 2024-03-06 | Michael Reed | Scheduled | Agenda to be shared prior to meeting.
Freelancer Task Pool | Budget Review | 2024-03-20 | 2024-03-25 | Jane Williams | Completed | Final budget adjusted and approved.