## Worksheet
Task | Start Date | End Date | Responsible Party | Resource Required | Status | Priority | Dependencies
Project Initiation | 2024-04-01 | 2024-04-10 | Project Manager | PM, Finance Lead | Completed | High
Requirement Gathering | 2024-04-11 | 2024-05-05 | Business Analysts | Stakeholders, Users | In Progress | High | Project Initiation
Design Phase | 2024-05-06 | 2024-06-15 | UX/UI Team | Design Tools, Developers | Planned | Medium | Requirement Gathering
Development Phase | 2024-06-16 | 2024-08-30 | Development Team | Backend, Frontend Engineers | Planned | High | Design Phase
Testing & QA | 2024-09-01 | 2024-09-30 | QA Team | Test Automation, Manual QA | Scheduled | High | Development Phase
Deployment & Go-Live | 2024-10-01 | 2024-10-15 | DevOps & IT Ops | Cloud Infrastructure, Support Team | Planned | High | Testing & QA