## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Priority | Notes
Resource Allocation Review | 2024-04-01 | 2024-04-05 | John Doe | In Progress | High | Review current team assignments and identify bottlenecks.
Equipment Procurement | 2024-04-10 | 2024-04-25 | Jane Smith | Pending | Medium | Purchase new printers and workstations.
Staff Training Plan | 2024-05-01 | 2024-05-15 | Mike Johnson | Not Started | High | Conduct training on new software and safety protocols.
Budget Forecasting | 2024-04-15 | 2024-04-30 | Sarah Lee | In Progress | High | Analyze cost trends and prepare quarterly forecast.