## Worksheet
Task ID | Task Name | Start Date | End Date | Responsible Person | Resource Required | Status | Priority
RPL-001 | Initial Resource Assessment | 2024-03-01 | 2024-03-15 | John Smith | HR, Finance | In Progress | High
RPL-002 | Equipment Procurement Plan | 2024-03-16 | 2024-04-10 | Sarah Lee | IT, Logistics | Planned | Medium
RPL-003 | Team Training Schedule | 2024-04-11 | 2024-05-15 | Mike Johnson | Training Staff | On Track | Low
RPL-004 | Performance Evaluation Cycle | 2024-05-16 | 2024-06-30 | Lisa Brown | HR, Management | Planned | High