## Worksheet
Task | Start Date | End Date | Responsible Person | Resource Allocation | Status | Priority
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | Jane Doe | Project Manager, Team Lead | On Track | High
Market Research Phase | 2024-03-05 | 2024-03-15 | John Smith | Research Team, Analysts | On Track | High
Design Development | 2024-03-18 | 2024-04-10 | Lisa Brown | Design Team, UI/UX Specialists | In Progress | High
Development Phase | 2024-04-11 | 2024-05-30 | Mark Lee | Engineering Team, DevOps | Planned | High
Testing & Quality Assurance | 2024-06-01 | 2024-06-30 | Sarah Kim | QA Team, Test Engineers | Not Started | High
Deployment & Launch | 2024-07-01 | 2024-07-15 | David Wong | IT Operations, Cloud Team | Planned | High