## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Status | Priority
Product Vision Finalization | Alex Chen | 2024-03-01 | 2024-03-15 | 15 | In Progress | High
Market Research & Analysis | Jordan Lee | 2024-03-16 | 2024-04-05 | 21 | On Track | Medium
UI/UX Design Sprint | Mia Rodriguez | 2024-04-06 | 2024-04-18 | 13 | Planned | High
Development Phase (MVP) | Team Lead Dev | 2024-04-19 | 2024-06-30 | 73 | Not Started | Critical
Beta Testing & Feedback Loop | Sarah Kim | 2024-07-01 | 2024-07-31 | 31 | Planned | Medium
Launch & Post-Launch Review | Marketing Director | 2024-08-01 | 2024-08-15 | 15 | Not Started | High