## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Status | Dependencies | Resources Required
Project Kickoff Meeting | Alex Johnson | 2024-04-01 | 2024-04-01 | 1 | Completed | - | Team Lead, Meeting Room
Requirement Gathering | Maria Lopez | 2024-04-02 | 2024-04-10 | 9 | In Progress | Kickoff Meeting | Stakeholders, Analysts
Design Phase Finalization | James Chen | 2024-04-11 | 2024-04-25 | 15 | Planned | Requirement Gathering | UI/UX Designer, Design Tools
Development Sprint 1 | Team A | 2024-04-26 | 2024-05-03 | 8 | Not Started | Design Finalization | Developers, Dev Environment
Testing & QA Review | Sophia Kim | 2024-05-04 | 2024-05-15 | 12 | Planned | Development Sprint 1 | QA Team, Test Cases
Deployment to Staging | David Ruiz | 2024-05-16 | 2024-05-17 | 2 | Not Started | Testing & QA Review | DevOps, Staging Server
User Training Session | Linda Patel | 2024-05-18 | 2024-05-18 | 1 | Scheduled | Deployment to Staging | Trainers, End Users