## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Progress (%) | Resource Allocation | Dependencies | Notes
T001 | Project Initiation Phase | John Doe | 2024-03-01 | 2024-03-15 | In Progress | 65% | Project Manager, 2 Analysts | None | Finalize scope document and stakeholder sign-off.
T002 | Resource Assessment & Allocation | Jane Smith | 2024-03-16 | 2024-04-10 | Planned | 30% | HR Team, 3 Developers | T001 | Review availability and skill sets.
T003 | Development Phase - Module A | Mike Johnson | 2024-04-11 | 2024-05-31 | Not Started | 0% | 5 Developers, 1 QA Engineer | T002 | Build core functionality for user dashboard.
T004 | Testing & Quality Assurance | Lisa Chen | 2024-06-01 | 2024-07-15 | Not Started | 0% | 3 QA Engineers, 2 Test Managers | T003 | Ensure compliance with user requirements.
T005 | Deployment & Go-Live | David Brown | 2024-07-16 | 2024-07-31 | Planned | 0% | DevOps Team, 2 Support Staff | T004 | Full system rollout to production environment.