## Worksheet
Task ID | Task Name | Assigned To | Priority | Due Date | Status | Resource Required | Estimated Hours | Actual Hours | Dependencies
T-001 | Project Kickoff Meeting | John Smith | High | 2023-10-05 | In Progress | Project Manager, HR Rep | 4 | 3.5 | None
T-002 | Market Research Analysis | Sarah Lee | Medium | 2023-10-15 | Not Started | Data Analyst, Market Expert | 8 | 0 | T-001
T-003 | Development Phase Planning | Mike Chen | High | 2023-11-01 | Planned | Software Engineer, QA Lead | 20 | 0 | T-002
T-004 | User Testing & Feedback Collection | Lisa Wong | Medium | 2023-11-20 | Not Started | UX Designer, Test Manager | 15 | 0 | T-003
T-005 | Final Documentation & Review | Anna Patel | Low | 2023-12-05 | Not Started | Technical Writer, Project Manager | 6 | 0 | T-004